## Sheet1
Risk register
Date: 12/08/2024
Outline of the document and template
Risk description: short description of the overview of the risk and why it’s a potential issue.
Risk category: Operations, Budget, Schedule, Technology, Information, Security, Quality, Project plan
Risk likelihood: Not likely, somewhat likely, likely, very likely
Risk analysis: Very low, low, medium, high, very high
Risk mitigation: response plan, a brief description of how to lessen the risk
Risk priority: 1 (low), 2 (medium), 3 (high)
Risk status: Communicate the status of the task, Open, in progress, and closed.
Risk | Risk description | Category | Likelihood | Analysis | Mitigation | Priority | Status
Data loss / Data privacy laws | Documents are not stored permanently on server database; documents will be stored as temporary files or in database and cleared once output is produced. This may lead to data loss if the process is interrupted. Must comply with legal and industry standard data privacy laws for the comfortability of client use of the application. | Technology, security, information, technical | Likely | High | Implement logging ensuring data is recoverable or reprocessed in the case of an interruption. Implement error handling for graceful error recovery. Consult client on data handling. | 3 (high) | Client instructed on not having data stored, must implement security measures for safe data handling.
Security of Temp files / Vulnerabilities in web application | Temporary files may be tampered with / accessed during processing. Web application may have vulnerabilities such as SQL injection, and Improper transport layer security. | Security, information, technical | Likely | High | Using secure isolated environment for temporary file storage, encryption and restricting access. Secure deletion after processing. Validate the input to prevent injection attacks. Implement tokens in forms, use HTTPS, and penetration testing. | 3 (high) | Discussed with client, in progress
Bottlenecking | Slow performance when processing many documents or multiple requests. | Performance, technology, technical | Likely | Medium | Optimize code, performance testing and benchmarking. Asynchronous processing for multiple requests. | 2 (medium) | Not implemented, open.
Client communication & engagement | Lack of communication with Client may result in unclear requirements and expectations of the application. | Information, operations, project plan | Not likely | Medium | Regular communication with client, provide progress updates with sprint deliverables and receive feedback to ensure correct requirements and functionality. | 3 (high) | First meeting went well, received all requirements. Need to determine budgeting and final requirements for next meeting. Next meeting 13/08/24, 10am.
Inadequate Testing coverage | Insufficient testing allowing undiscovered vulnerabilities or bugs in the frontend affecting user friendliness, and vulnerabilities in data processing and handling. | Technical, Information, Security | Not likely | High | Develop comprehensive testing strategy using, system testing, user acceptance testing, functional testing, integration testing, unit testing, and performance testing. | 2 (medium) | To be implemented in sprint 3 during testing of application. Open
Team skill gaps | Lack of skills necessary for the development of the project within the team. Would lead to quality issues, or delays. | Technical | Not likely | Medium | Conduct skill audit and ensure learning of skills required for development of the application. Ensure members are given tasks that complement their skills. | 2 (medium) | Audit has been completed. Closed.
Change in project scope | Changes in the project scope via client or external factors could lead to scope creep and strain on resources. | Project plan. Schedule, Operations | Likely | Medium | Implement a process to evaluate and approve scope changes such as budgeting of requirements. Ensure clear documentation of the project requirements and task objectives. | 3 (high) | Budgeting of requirements yet to be done, Requirements clearly documented and task objectives available on github. In progress.
Scheduling conflicts & Project management | Unclear leadership could lead to confusion and inefficiencies through clashing of members and tasks. Must have clear project direction and ensure members are working on something in conjunction. | Project plan, Operations | Somewhat likely | High | Develop project schedule, ensuring communication between members and tasks. | 2 (medium) | Github project plan implemented for tasks, tasks in progress, and completed tasks. In progress.
Integration issues | Integration issues if connecting our application with other services. Specifically, may occur when integrating with document storage, third party APIS used in document parsing such as XML or python docx. | Technical | Somewhat likely | Medium | Identify all external services or API’s needed for the application. Use standard data formats such as JSON, and XML for interoperability. Implement graceful error recovery to manage failures of communication or data inconsistencies. | 2 (medium) | In progress.
Third party services – APIS | Usage of API’s or third-party services may introduce unreliability of services change unexpectedly, may introduce unreliability and bugs. | Technology, Technical | Not likely | Low | Evaluate reliability of third-party services before implementation / integration. Have a plan in case of failure or disruption | 1 (low) | Not implemented.
User adoption | Client may resist using the new application if the existing application is more useful. | Quality | Not likely | Medium | Engage with the client in development to receive feedback and let them guide the needs and wants of the application in the development process. | 2 (medium) | Feedback to be received in next meeting, based on the example user interface.
Unclear requirements | Aligns with change in project scope risk and client communication, Changes in the requirements may lead to a different product to what was proposed by the client. | Project plan | Not likely | Low | Clear documentation of project requirements. Regular reviews and updates of the requirements with client | 2 (medium) | Draft requirements received, need to be finalized for tomorrow 13/08/24
Budget constraints (Requirements budget) | Based off of the $100 budget given to the client and assigned to each main requirement for the project. Focusing on the higher priority requirements may affect development of the lower budgeted requirements. | Budget, Schedule | Not likely | Low | Implement management practices ensuring that all necessary requirements are completed. | 2 (medium) | Budget of requirements yet to be done by client.
Data compatability issues | Differences in document formats may cause compatability issues with incorrect processing or loss of information. | Technical, Information | Somewhat likely | Medium | Implement compatability testing for different documents and versions, may not be required as assuming we are only using docx files. | 2 (medium) | In progress. No tests conducted as of now.
Scalability and performance | As volume data increases, may want to compare more than two documents as one per the clients request. This will introduce performance degradation and slow process times for comparisons between documents | Technical, Performance | Likely | High | Implement performance optimization such as caching, load balancing and code refactorisation. Use scalability testing to ensure application can handle expected future growth | 3 (high) | Not implemented. Scalability tests in phase 3 after first revision.
Data quality issues | Incomplete information / incorrect information could lead to inaccurate results of the application. Includes mainly incosistent or missing RSID codes | Information, Quality | Not likeyl | Medium | Implement data validation and cleansing process of input data. | 2 (medium) | In progress, Data validation as .docx in the frontend dropbox implemented.